CITY OF DANA POINT

Reviewed By:

DH 	___

CM 	___

CA	___

X

X

AGENDA REPORT

# DATE:	FEBRUARY 16, 2016

TO:		CITY MANAGER/CITY COUNCIL

## FROM 	CYNTHIA NELSON, INTERIM ECONOMIC DEVELOPMENT MANAGER

SUBJECT:	DOHENY VILLAGE PLAN UPDATE

RECOMMENDED ACTION:

Receive and file.

BACKGROUND:

In keeping with City Council’s direction, the subject agenda item is the monthly report outlining efforts since the last update to advance the completion of the Plan.

DISCUSSION:

Land Use Plan/Development Standards

Opticos is drafting the code language for Doheny Village and is on schedule to deliver the Administrative Draft Code and Regulating Plan in mid-March.  Both the City Council and Planning Commission recently appointed two members each to serve on the Code Committee to provide feedback during the development of the code standards.  The City Council appointed Mayor Tomlinson and Council Member Muller; the Planning Commission appointed Scott McKhann and Danni Murphy.  Staff is in the process of confirming participation of up to two developers and up to two architects.   In addition, Staff will begin the solicitation of interest from an at-large resident and a business owner located in Doheny Village.  Information pertaining to the opportunity to participate will be posted on the City’s website, as well as email notifications and mailings to parties previously notified during the planning Charrette last fall.  It is expected the Code Committee will be convened for three meetings between May 1 and 15.  Opticos will then prepare the Public Draft Code and Regulating Plan and submit the final draft documents to the City by June 3.

Environmental Impact Report

Michael Baker International (MBI) has commenced preparation of the Initial Study and Notice of Preparation for the Program Environmental Impact Report (“EIR”).  A more refined project schedule is being developed, with the final draft EIR expected to be completed in late 2016.  The Capistrano Unified School District notified the City in January of its desire for the City to designate their property in the Plan as “mixed-use development” as opposed to higher density residential as originally contemplated.  A meeting with the Superintendent and City Staff to discuss their request has been set for February 19, 2016.   The project description for the EIR cannot be completed until there is final resolution as to the land use designation for this property; therefore, the original EIR schedule will be impacted by this delay.

Community Outreach

As mentioned above, Staff will be meeting the CUSD representatives to further discuss the future development options for the bus yard property.  Staff is also reaching out to qualified developers and architects to serve on the Code Committee.

Outreach efforts continue with developers, brokers, tenants and property owners to engage them to consider investing in the Village, whether it is now under current zoning, or after the new Plan is approved.  Staff is continuing discussions with Capo Beach Church on their expansion plans.

Staff continues to communicate regularly with Capo Cares, area residents and businesses to discuss the planning process and other issues in the area, such as public improvements, public safety, area cleanliness, community events, etc.

STRATEGIC PLAN:

The proposed actions are consistent with the Strategic Plan Initiative to evaluate land use issues to ensure that the goals of the General Plan reflect the community’s vision and mission and to foster a vibrant business climate.

FISCAL IMPACT:

There is no fiscal impact associated with this action; however, in an effort to keep the City Council apprised of expenditures related to the planning process, summarized below are existing contract encumbrances and other miscellaneous expenses to date:

| Doheny Village Project Budget Summary |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  | Contract Amount |
| Keyser Marston Associates |  | Economic Analysis |  | $38,000.00 |
| Opticos Design, Inc. |  | Form-Based Code |  | $229,472.00 |
| JLC Engineering |  | Hydraulic Analysis |  | $42,500.00 |
| Nelson/Nygaard Consulting Associates |  | Traffic Study |  | $93,180.00 |
| Michael Baker International |  | EIR |  | $169,833.00 |
| Hetherington Coastal Geotechnical |  | Geotechnical Consultant |  | $17,000.00 |
| David Evans & Associates |  | Right of Way Surveying |  | $50,000.00 |
| Linscott, Law & Greenspan |  | Traffic Engineers |  | $77,600.00 |
| Charrette Incidentals |  |  |  |  |
| Materials, Meals and Advertising |  |  |  | $8,670.00 |
|  |  | Total Expenses |  | $726,255.00 |